## Gantt Chart
SCHEDULE BASELINE (GANTT CHART)
Task Name | Assigned To | Start (Date) | End (Date) | Duration (Days) | Percentage of Completion
Define survey questions | Phuong Tran | 2024-09-28 | 2024-10-01 | 3 | 100%
Test and finalize survey tool | Phuong Tran & Devansh Sharma | 2024-10-02 | 2024-10-03 | 1 | 100%
Generate and print QR codes | Devansh Sharma | 2024-10-04 | 2024-10-05 | 1 | 100%
Organize survey distribution at Riverside Campus | Keying Wang & Gaurav Singh | 2024-10-06 | 2024-10-06 | 0 | 100%
Conduct surveys at Riverside Campus | Ramandeep Singh | 2024-10-07 | 2024-10-07 | 0 | 100%
Conduct surveys at fitness center and cafeteria | Keying Wang & Phuong Tran | 2024-10-08 | 2024-10-09 | 1 | 100%
Clean and preprocess survey data | Phuong Tran | 2024-10-11 | 2024-10-11 | 0 | 100%
Perform statistical analysis | Keying Wang | 2024-10-12 | 2024-10-13 | 1 | 100%
Draft survey results | Ramandeep Singh | 2024-10-14 | 2024-10-16 | 2 | 100%
Review and finalize report | Keying Wang & Phuong Tran | 2024-10-17 | 2024-10-17 | 0 | 100%
Prepare final presentation | All team members (led by Keying Wang) | 2024-11-06 | 2024-11-19 | 13 | 100%