## Stakeholder Register
STAKEHOLDER REGISTER |  |  | COMMUNICATION STRATEGY |  |  |  | ENGAGEMENT ACTIVITIES
Stakeholder | Role/Responsibility | Contact Method | Activity | Stakeholder(s) Involved | Method of Communication | Frequency | Activity | Stakeholder(s) Involved | Description | Frequency
Project Team Members | Team members responsible for execution | Email, Group Chat, Meetings | Weekly Progress Reports | Project Team, Professor Pratik Bedi | Email | Weekly | Sending Survey for Feedback | Survey Participants, Project Team | Survey feedback to improve quality | By October 10th, 2024
Keying Wang (Team Leader) | Oversees data collection and overall progress | Email, Group Chat, Meetings | Milestone Reviews | Project Team, Professor Pratik Bedi | Meetings, Email Reports | At each project milestone | Milestone Review Meetings | Project Team, Professor Pratik Bedi | Discuss progress and adjustments | After each milestone
Professor Pratik Bedi | Project Sponsor and Instructor | Email, Office Hours, Meetings | Survey Distribution Updates | Project Team, Professor Pratik Bedi | Email, Meetings | As needed | Final Review and Feedback | External Reviewers, Professor Pratik Bedi | Provide final feedback on report | Before final submission
Survey Participants | Provide survey data | Google Form (QR Codes) | Final Presentation | Project Team, Professor Pratik Bedi, External Reviewers | Presentation, Email | November 18th, 2024
External Reviewers | Provide feedback on the final project report | Email, Review Meetings
PROJECT TEAM MEMBERS
|  |  | Role | Responsibilities
|  |  | Project Leader (Keying Wang) | Oversight of all communication channels, ensuring timely updates, weekly reporting to stakeholders, and resolving escalated issues.
|  |  | Survey Designer (Tran Bao Diem Phuong) | Communicate survey design progress to stakeholders, address feedback, and ensure clarity.
|  |  | Tech Support (Devansh Sharma) | Distribute survey links and QR codes, provide technical support, and resolve any issues that arise during data collection.
|  |  | Data Collectors (Gaurav Singh, Ramandeep Singh) | Provide real-time updates on data collection progress and any challenges through group chats.
|  |  | Data Analyst (Tran Bao Diem Phuong) | Report findings during the analysis phase and share insights via Tableau dashboards.
|  |  | Report Writer (Gaurav Singh) | Prepare the final report, ensuring timely stakeholder review and approval.