## Sheet1
Resource Work Activities Chart |  |  |  | Resource Allocation Table
Task | Resource(s) Responsible | Timeline | Notes | Resource Type | Details | Assigned Personnel | Timeline | Tools/Equipment
Survey Design | Keying Wang | September 28 - October 10 | Finalize survey design after feedback. | Personnel | Tasks assigned based on roles; monitor workload balance. | Project Leader (Tran Bao Diem Phuong), Survey Designer (Keying Wang), Tech Support (Devansh Sharma), Data Collectors (Gaurav Singh, Ramandeep Singh), Data Analyst (Tran Bao Diem Phuong), Report Writer (Gaurav Singh) | Ongoing throughout project | N/A
Data Collection | Gaurav Singh, Ramandeep Singh | October 10 - October 20 | Coordinate survey distribution and data collection. | Time | Assign realistic timeframes based on availability. | All team members | September 28 - November 10 | N/A
Data Validation | Gaurav Singh, Ramandeep Singh | October 10 - October 20 | Ensure data accuracy and completeness. | Tools/Equipment | Software and hardware to be used during project phases. | Tableau (for data analysis), laptops (for data collection), QR codes (for survey distribution) | As per task schedule (see timeline) | Tableau, laptops, QR codes, Google Drive
Data Analysis | Tran Bao Diem Phuong | October 20 - October 25 | Analyze collected data and identify insights. | Physical Resources | Ensure availability of physical resources during key phases. | All team members | During data collection and analysis phases | QR codes, any printed materials
Report Writing | Gaurav Singh | October 25 - November 5 | Write final report, incorporating data analysis findings.
Final Presentation Preparation | Keying Wang, Tran Bao Diem Phuong | November 5 - November 10 | Prepare for presentation to stakeholders. | Resource Constraints
|  |  |  | Resource Type | Constraint | Impact | Mitigation Strategy
|  |  |  | Personnel | Limited availability of team members (e.g., during report writing phase). | Delays in report preparation or analysis if team members are unavailable. | Adjust timeline, ensure workloads are balanced, and plan for overlapping tasks.
|  |  |  | Time | Tight project deadlines (e.g., for final report submission). | Risk of rushed work or incomplete tasks at the final stages. | Monitor progress closely, break down tasks into manageable parts, and ensure buffer time for unexpected delays.
|  |  |  | Tools/Equipment | Need for software tools like Tableau for visualization. | Delays in data analysis or presentation if tools are unavailable. | Early acquisition of software licenses and scheduled training for team members.
|  |  |  | Physical Resources | Limited access to QR codes or hardware. | Delays in survey distribution or data collection. | Ensure timely procurement and pre-setup before starting data collection.